## Task List
VF-OPS-001 — Implementation Task List
ID | Title | Description | Acceptance Criteria | Epic | Role | SP | Priority | Sprint | Dependencies | Status | Notes
DB-01 | Prisma schema — base PPM models | Implement core models: Project, ProjectTask, RAIDItem, ProjectBudget, ResourceAssignment. Add all enums (TaskStatus, RAGStatus, RAIDType, Priority). | Schema migrates without errors. All relations (Owner, Assignee, Project) resolve correctly. Enums validated. | Epic 1: Foundation | DB | 5 | P0 | Sprint 1 |  | Not Started | Must be authored before Sprint 1 begins. Schema gap was critical blocker in v1 spec.
DB-02 | Prisma schema — premium models | Add Milestone, ProjectDependency, GateReview, DecisionRecord, SprintRecord, CycleTimeLog, ProjectForecast, ProjectInsight, ProjectBaseline, UserSkill, Capacity models. | All new models migrate. Foreign key relations verified. No breaking changes to base schema. | Epic 1: Foundation | DB | 8 | P1 | Sprint 1 | DB-01 | Not Started | Tier 1–5 premium features all depend on these models.
DB-03 | Seed script — initial data | Create seed script for default project statuses, priorities, sample projects, and OKR objectives. | Running prisma db seed populates all lookup tables. Sample data usable in dev/staging. | Epic 1: Foundation | DB | 2 | P1 | Sprint 1 | DB-01 | Not Started
INF-01 | S3 configuration for project files | Create /projects/attachments/ folder in S3. Update IAM policies to allow backend write access. Block public access. | Backend can write to new folder. Public access blocked and verified. File type validation enforced at IAM level. | Epic 1: Foundation | DEVOPS | 2 | P0 | Sprint 1 |  | Not Started | Required before BE-07 (file attachment service).
INF-02 | Notification service integration | Configure email service integration with VF-LEG-001 shared notification service. Document API contract. Implement test harness. | Test email sends successfully from backend. Contract with shared service documented and signed off. | Epic 1: Foundation | BE | 3 | P1 | Sprint 1 |  | Not Started | Dependency contract with VF-LEG-001 must be agreed in Sprint 0 before this ticket is started.
INF-03 | Shared User Model contract | Document the interface between PPM and the shared User Model from VF-LEG-001. Define which fields PPM extends, which role enum values are shared, and how JWT claims are structured. | Written contract signed off by CLM and PPM leads. Prisma schema reflects agreed shared fields. No duplication of user data. | Epic 1: Foundation | BE | 2 | P0 | Sprint 0 |  | Not Started | Sprint 0 pre-requisite. Blocks all RBAC implementation.
BE-01 | Project CRUD endpoints | Create REST endpoints to create, read, update, and archive projects. Owner assignment enforced on creation. Baseline snapshot created on project approval. | POST/GET/PATCH endpoints work. Owner assignment enforced. Baseline snapshot written to ProjectBaseline on status change to APPROVED. | Epic 2: Backend | BE | 5 | P0 | Sprint 1 | DB-01 | Not Started
BE-02 | RAG calculation engine | Implement auto-calculation of Project.ragStatus based on task overdue counts, RAID priorities, and budget variance. Priority order: RED > AMBER > GREEN. Initial state GREEN. Auto-revert on resolution. | All edge cases in §2.1.3 pass. Priority order correct. Initial state GREEN on project creation. Auto-revert verified. Manual override requires Admin + audit log entry. | Epic 2: Backend | BE | 8 | P0 | Sprint 2 | BE-01, DB-01 | Not Started | Trigger: task status change, task due date pass, RAID item creation/update, budget variance change.
BE-03 | Kanban state machine | Implement full 5-state task transition machine: TODO, IN_PROGRESS, IN_REVIEW, BLOCKED, DONE. Enforce valid transitions per matrix. Allow backward transitions per matrix. Validate blockers before DONE. | All 5 states implemented. Invalid transitions rejected (HTTP 422). Backwards transitions allowed per matrix. Blocker check prevents DONE when blockers active. PM/Admin required to reopen DONE. | Epic 2: Backend | BE | 5 | P0 | Sprint 1 | DB-01 | Not Started | State machine matrix defined in §2.2.4 of spec.
BE-04 | RAID log management | Implement CRUD for Risks, Actions, Issues, and Decisions. Decision register fields (optionsConsidered, rationale, approvedById) included. Priority sorting. Link RAID items to timeline date for Gantt flag rendering. | All four RAID types work. Decision register fields stored and returned. Priority sorting works. loggedDate stored for Gantt flag positioning. | Epic 2: Backend | BE | 5 | P1 | Sprint 2 | BE-01 | Not Started
BE-05 | Budget tracking service | Implement allocated vs spent tracking. Calculate variance %. Trigger AMBER alert at 5–10% variance. Trigger RED alert and RAG recalculation at >10% variance. Require receipt upload above configurable threshold. | Variance calculated correctly. AMBER/RED thresholds trigger alerts and RAG recalculation. Receipt requirement enforced above threshold. All budget changes audit logged. | Epic 2: Backend | BE | 5 | P1 | Sprint 2 | BE-01, BE-02 | Not Started
BE-06 | Resource assignment service | Implement endpoints to add/remove team members to projects. Store allocation %. Compute overallocation flag when user's total allocation across projects exceeds 100%. | Users linked to projects. Allocation % stored. Overallocation flag computed and exposed in API response. Notification triggered on overallocation. | Epic 2: Backend | BE | 3 | P1 | Sprint 2 | DB-01 | Not Started
BE-07 | File attachment service | Implement S3 upload logic for project files. Validate permitted file types and size limits. Store S3 URL in DB. Handle upload failures gracefully. | Files upload to S3. URL stored in DB. Permitted types enforced (PDF, DOCX, XLSX, PNG, JPG — max 25MB per file, 500MB per project). Upload failures return actionable error. S3 deletion on project archive. | Epic 2: Backend | BE | 5 | P0 | Sprint 2 | INF-01 | Not Started | File type/size limits must be formally defined before development — see §2.2.5 of spec.
BE-08 | Audit logging interceptor | Create NestJS interceptor to log all state-changing actions to ProjectAuditLog. Entries must be immutable (no UPDATE/DELETE endpoints exposed). | Every state change creates an audit log entry with userId, action, previousValue, newValue, timestamp. No DELETE/PUT endpoints on AuditLog. Verified in QA-06. | Epic 2: Backend | BE | 5 | P1 | Sprint 2 | DB-01 | Not Started
BE-09 | Portfolio aggregation API | Create cached endpoint returning aggregate data for the dashboard: RAG heatmap counts, delivery gauge (% on time), budget overview (total allocated vs spent), OKR coverage %, utilisation summary. | Returns all aggregate stats in a single call. Cache invalidation on project RAG change. Response time < 500ms P95 at 500 projects. | Epic 2: Backend | BE | 5 | P0 | Sprint 2 | BE-01, BE-02 | Not Started
BE-10 | Gantt data API | Create endpoint returning all data needed for Gantt rendering: project bars (start/end dates), milestones, dependency edges, forecast zones (from ProjectForecast), RAID flags (from RAIDItem.loggedDate and priority), baseline ghost bars. | All six Gantt signal types returned correctly. Filtered by user visibility. Response optimised for 100+ projects. | Epic 2: Backend | BE | 8 | P1 | Sprint 3 | BE-01, BE-11, BE-12 | Not Started | Frontend Gantt (FE-04) depends on this endpoint shape being stable.
BE-11 | Cross-project dependency engine | Implement ProjectDependency CRUD (FTS, STS, FTF types). On date change, perform topological sort of dependency graph and cascade date changes to downstream dependents. Notify downstream project owners. | Dependency CRUD works. Topological sort correctly identifies critical path. Date cascade triggers notifications. Circular dependency detected and rejected. | Epic 2: Backend | BE | 8 | P1 | Sprint 3 | DB-02 | Not Started | Topological sort must be proven in isolated spike before integration. Scope BE-GANTT-SPIKE separately if needed.
BE-12 | Monte Carlo forecast service | Calculate P50, P85, P95 delivery date estimates using N=10,000 simulations sampling from SprintRecord historical throughput distribution. Store in ProjectForecast. Nightly recalculation job. Suppress output if fewer than 3 sprints of data. | P50/P85/P95 computed correctly against test dataset. Confidence indicator suppressed below data threshold. Nightly job runs without timeout. Results stored and returned by Gantt API. | Epic 2: Backend | BE | 13 | P1 | Sprint 4 | DB-02, BE-10 | Not Started | Requires SprintRecord data from at least 3 sprints. Display confidence indicator in UI. Do not expose forecast until minimum threshold met.
BE-13 | Gate review workflow | Implement GateReview CRUD. Enforce required approvers list. Failed gate blocks downstream phase progression unless waived by Admin. All outcomes audit logged. | Gate CRUD works. Required approvers enforced. Failure blocks progression (HTTP 403 on next-phase request). Waiver requires Admin role + reason. Audit log entry on every outcome. | Epic 2: Backend | BE | 8 | P1 | Sprint 4 | DB-02, BE-08 | Not Started
BE-14 | Capacity planning service | Aggregate weekly resource allocation per user across all projects. Expose capacity vs demand view. Flag overallocation above configurable threshold. | Weekly allocation correctly aggregated. Overallocation threshold configurable per organisation. API response consumable by FE-12 capacity grid. | Epic 2: Backend | BE | 5 | P2 | Sprint 4 | BE-06, DB-02 | Not Started
BE-15 | OKR alignment service | Implement Objective and KeyResult CRUD. ProjectObjectiveLink model. OKR coverage calculation endpoint. Contribution score (0–100) per project-objective link. | OKR CRUD works. Coverage % calculated correctly. Contribution scores stored and returned. Portfolio dashboard receives OKR data. | Epic 2: Backend | BE | 5 | P2 | Sprint 4 | DB-02 | Not Started
BE-16 | Export service — PDF and CSV | Implement project export in PDF and CSV formats. Define fields included, formatting standards. Access control: PM and Stakeholders (own projects only). | PDF export renders correctly with all defined fields. CSV export is parseable. File size limits enforced. Access control verified. Export time < 30s P95. | Epic 2: Backend | BE | 5 | P1 | Sprint 3 | BE-01, BE-04, BE-05 | Not Started | Fields and formatting must be defined before development — see §2.2.5 of spec.
BE-17 | Notification preferences service | Allow users to configure notification preferences: instant vs daily digest per notification type. PM can configure project-level alert thresholds. | Preferences stored per user. Digest job batches instant notifications correctly. Project-level thresholds override system defaults. | Epic 2: Backend | BE | 3 | P2 | Sprint 4 | INF-02 | Not Started | Addresses notification fatigue risk in §6.
FE-01 | Portfolio dashboard page | Build /ops/portfolio/dashboard with RAGHeatmap (grid of projects coloured by status), DeliveryGauge (% on-time), BudgetOverview (allocated vs spent), OKRCoverageRing, semantic filter pills. | All five components render correctly. Filter pills (All, Engineering, PMO, At Risk) work. At Risk filter shows only Amber/Red. Data refreshes on project RAG change. | Epic 3: Frontend | FE | 8 | P0 | Sprint 2 | BE-09 | Not Started
FE-02 | Project workspace layout | Build /ops/projects/[id] with tabbed navigation: Kanban, RAID, Budget, Files, Gates, Decisions. ProjectHeader shows RAG status, owner, dates, health score, forecast date. | Tabs switch content without full reload. Header shows all six data points. RAG status colour-coded. Forecast confidence indicator shown. | Epic 3: Frontend | FE | 5 | P0 | Sprint 2 | BE-01 | Not Started
FE-03 | Kanban board component | Build drag-and-drop Kanban using @dnd-kit. Five columns matching state machine (TODO, IN_PROGRESS, IN_REVIEW, BLOCKED, DONE). Optimistic UI update. Blocker indicator on cards. WIP limit display. | Tasks move between valid columns. Invalid transitions prevented with user-facing error. Blocker icon shown on BLOCKED cards. Optimistic update with rollback on failure. | Epic 3: Frontend | FE | 13 | P0 | Sprint 2 | BE-03, FE-02 | Not Started
FE-04 | Gantt chart — static rendering | Build custom SVG Gantt with: bar rendering (coloured by RAG), progress fill layer (35% opacity), today line, milestone diamonds (pulse if overdue), RAID risk flags, dependency Bezier curves, baseline ghost bars, slip zones. Time scale toggle (Month/Quarter/Year). Semantic filter pills. | All seven premium signal types render correctly. Today line positioned accurately. Milestone diamonds pulse when overdue. RAID flags show tooltip on hover. Slip zone appears when forecast > planned end. Baseline ghost bars visible behind current bars. | Epic 3: Frontend | FE | 21 | P0 | Sprint 3 | BE-10 | Not Started | Highest SP ticket in the project. This is the premium differentiator. Do NOT use a third-party Gantt library — custom SVG/Canvas only.
FE-05 | Gantt chart — drag-to-reschedule | Add drag handles to Gantt bars. On drag, call BE-11 topological sort. Cascade date changes to downstream bars with animation. Show constraint violation warning before confirm. | Bar drag updates project dates. Downstream bars animate to new positions. Constraint violation modal shown before confirmation. Undo available for 30 seconds. | Epic 3: Frontend | FE | 13 | P1 | Sprint 4 | FE-04, BE-11 | Not Started | Gate behind separate feature flag. BE-11 topological sort must be stable before this is started.
FE-06 | RAID log data grid | Build table for RAID items with filters (Type: R/A/I/D, Priority, Status). Inline status editing. Decision register tab with full decision fields. RAID item creation modal. | All four RAID types filterable. Inline status edit saves without full reload. Decision register shows all fields from DecisionRecord model. Creation modal validates all required fields. | Epic 3: Frontend | FE | 8 | P1 | Sprint 3 | BE-04, FE-02 | Not Started
FE-07 | Budget chart component | Build line/bar chart for Planned vs Actual spend. Variance % highlighted amber at 5–10%, red above 10%. Receipt upload link per spend entry. Budget history timeline. | Chart renders with correct data. Variance thresholds colour-coded correctly. Receipt upload opens file picker linked to BE-07. Chart updates on spend entry. | Epic 3: Frontend | FE | 5 | P1 | Sprint 3 | BE-05, FE-02 | Not Started
FE-08 | Project creation wizard | Build 5-step form: Details → OKR Link → Budget → Team → Gate Configuration. Each step validates before advance. Summary review before submit. | All 5 steps validate inputs before advancing. OKR selector shows active objectives. Team member search works. Gate configuration optional but saves if provided. Summary step shows all inputs before final submit. | Epic 3: Frontend | FE | 8 | P0 | Sprint 3 | BE-01, BE-15 | Not Started
FE-09 | Task detail modal | Build modal opening from Kanban card. Shows task details, state transition buttons (per state machine), comments thread, file attachments, cycle time, assignee. | Modal opens without page reload. State transition buttons show only valid next states. Comments save in real time. File attachment uploads via BE-07. Cycle time displayed. | Epic 3: Frontend | FE | 5 | P1 | Sprint 3 | BE-03, BE-07, FE-03 | Not Started
FE-10 | RBAC frontend guards | Implement route guards and component-level permission checks based on RBAC matrix in §2.2.3. All four roles tested: Admin, PM, Member, Stakeholder. | All buttons, tabs, and routes hidden/disabled per permission matrix. Tested for all four roles. Budget tab invisible to Members and Stakeholders. Manual RAG override button visible to Admin only. | Epic 3: Frontend | FE | 5 | P0 | Sprint 2 | INF-03 | Not Started | Permission matrix in §2.2.3 of spec is the authoritative reference.
FE-11 | File upload component | Build drag-and-drop upload zone for project attachments. Show upload progress. Validate file type and size client-side. File list updates on success. Delete with confirmation. | Drag-and-drop works. Upload progress shown. Client-side type/size validation matches server-side rules. File list reflects upload result. Delete requires confirmation. | Epic 3: Frontend | FE | 3 | P1 | Sprint 3 | BE-07 | Not Started
FE-12 | Capacity planning grid | Build weekly grid showing each person's allocated % vs available hours across all their projects. Overallocation (>100%) highlighted red. Skill badges per person. Filterable by team. | Weekly allocation shown per person. Overallocation highlighted in red. Skill badges display top 3 skills. Team filter works. Grid scrollable horizontally for 12-week view. | Epic 3: Frontend | FE | 8 | P2 | Sprint 4 | BE-14, FE-01 | Not Started
FE-13 | Dependency graph view | Build directed graph visualisation alongside Gantt. Nodes coloured by RAG status. Edges show dependency type. Critical path highlighted on milestone hover. | Graph renders all project nodes and dependency edges. RAG colours applied to nodes. Critical path highlights in distinct colour on hover. Zoom and pan functional. | Epic 3: Frontend | FE | 13 | P1 | Sprint 4 | BE-11, FE-04 | Not Started
FE-14 | Public status page builder | Build configurable external-facing page at /ops/projects/[id]/status. Auto-populated from project data. PM adds optional commentary. Shareable link with optional password. Mobile-friendly. | Page renders without authentication. PM can toggle which sections are visible. Commentary field saves. Shareable link generated. Optional password protection works. | Epic 3: Frontend | FE | 8 | P2 | Sprint 5 | BE-01, FE-02 | Not Started
FE-15 | Gate review panel | Build gate review interface within project workspace. Entry/exit criteria checklist. Approve/Fail/Waive action buttons. Required approvers list with status badges. Gate history. | Criteria checklist interactive. Approve/Fail buttons trigger BE-13 workflow. Waive button visible to Admin only. Approver list shows who has/hasn't acted. Gate history shows all past outcomes. | Epic 3: Frontend | FE | 5 | P1 | Sprint 4 | BE-13, FE-02 | Not Started
FE-16 | Velocity analytics dashboard | Build sprint-over-sprint throughput charts, cycle time scatter plot, and cumulative flow diagram (CFD). All charts filterable by date range. | Throughput bar chart renders with trend line. Cycle time scatter plot highlights outliers (>2x median). CFD shows column distribution over time. Date range filter works. | Epic 3: Frontend | FE | 8 | P2 | Sprint 5 | BE-12 | Not Started
FE-17 | Prioritisation scoring matrix | Build value vs effort 2x2 matrix view. Projects plotted as bubbles sized by budget. Score calculation using configurable weight coefficients (value, strategic fit, risk, effort). | 2x2 matrix renders with project bubbles. Bubble size proportional to budget. Score formula uses configurable weights. PMO Admin can edit weight coefficients. Quadrant labels shown. | Epic 3: Frontend | FE | 8 | P2 | Sprint 5 | BE-15 | Not Started
SEC-01 | API role guards | Implement NestJS guards: AdminGuard, PMOGuard, ProjectManagerGuard, MemberGuard, StakeholderGuard. Apply to all endpoints per RBAC matrix §2.2.3. | All unauthorised requests return 403. Guards tested for all four roles against every endpoint in §4.3. No elevation of privilege possible. | Epic 4: Security | BE | 5 | P0 | Sprint 1 | INF-03 | Not Started | RBAC matrix in §2.2.3 is the authoritative reference. Must be signed off before implementation.
SEC-02 | Budget data access control | Ensure Budget fields and endpoints are accessible only to Finance/PM roles. API returns 403 for Members and Stakeholders. | Budget endpoints return 403 for Member and Stakeholder roles. Verified in integration tests for all four roles. Budget tab hidden in FE-10. | Epic 4: Security | BE | 3 | P1 | Sprint 2 | SEC-01 | Not Started
SEC-03 | Audit log integrity enforcement | Ensure ProjectAuditLog has no DELETE or PUT endpoints. Entries are immutable after creation. Verify in penetration test QA-06. | No DELETE/PUT endpoints exposed for AuditLog. API returns 405 Method Not Allowed. Verified in QA-06 security pen test. | Epic 4: Security | BE | 2 | P0 | Sprint 1 | BE-08 | Not Started
SEC-04 | Data isolation — project visibility | Ensure users can only query projects they are assigned to unless they have Admin or PMO role. Apply ownership/assignment filter to all project queries. | All project list and detail queries filtered by assignment. Admin/PMO bypass verified. Unauthorised project access returns 404 (not 403, to avoid enumeration). | Epic 4: Security | BE | 5 | P0 | Sprint 1 | DB-01 | Not Started | Return 404 not 403 to prevent project ID enumeration.
SEC-05 | OpenAPI spec generation | Generate and publish OpenAPI 3.0 specification for all endpoints in §4.3. Include request/response schemas, error codes, and auth requirements. | OpenAPI spec generated and accessible at /api/docs. All 11+ endpoints documented with full schema. Spec validated with no errors. Updated automatically on deployment. | Epic 4: Security | BE | 5 | P0 | Sprint 1 | BE-01 | Not Started | This was a critical gap in the v1 spec. Must be done before FE begins building against the API.
SEC-06 | Manual RAG override controls | Implement Admin-only manual RAG override endpoint. Require reason code. Enforce audit log entry. Build override UI visible only to Admin role. | Override endpoint requires Admin JWT. Reason code is mandatory (HTTP 422 if absent). Audit log entry created with overriding userId, reason, previous value. Override visible in project audit trail. | Epic 4: Security | BE+FE | 3 | P1 | Sprint 2 | BE-02, SEC-01 | Not Started
QA-01 | Unit tests — RAG logic | Write Jest unit tests for all RAG calculation scenarios including all edge cases defined in §2.1.3: simultaneous conditions, initial state, auto-revert, budget AMBER/RED thresholds. | Code coverage >80% for RAG engine. All edge cases in §2.1.3 have explicit test cases. Priority order (RED > AMBER > GREEN) verified. | Epic 5: QA & Testing | QA/BE | 5 | P1 | Sprint 2 | BE-02 | Not Started
QA-02 | Unit tests — Kanban state machine | Write Jest tests for all state transitions in the 5-state machine including backward transitions and blocker validation. | All valid transitions have passing tests. All invalid transitions have rejection tests. Backward transition conditions verified. Blocker check for DONE verified. | Epic 5: QA & Testing | QA/BE | 3 | P1 | Sprint 2 | BE-03 | Not Started
QA-03 | Integration tests — core flows | Test end-to-end API flows: (1) Create Project → Add Task → Make Overdue → Verify RAG changes to Amber then Red. (2) Update Budget → Exceed 10% → Verify alert triggered and RAG recalculated. | Both flows pass consistently in CI. All endpoints return expected status codes. RAG transitions verified against database state. Alert delivery verified. | Epic 5: QA & Testing | QA/BE | 8 | P1 | Sprint 3 | BE-01, BE-02, BE-05 | Not Started
QA-04 | Integration tests — RBAC flows | Test all four roles (Admin, PM, Member, Stakeholder) against all endpoints in §4.3. Verify 403/404 responses for unauthorised access patterns. | All four roles tested against all endpoints. No role can access a resource it should not. No role is blocked from a resource it should have. Verified in CI. | Epic 5: QA & Testing | QA/BE | 5 | P1 | Sprint 3 | SEC-01, SEC-04 | Not Started
QA-05 | E2E test — Kanban workflow | Playwright script: Login as PM → Create task → Move task through states → Attempt invalid transition → Verify DB state. Test with blocker active. | Script passes consistently in Staging. Invalid transition correctly blocked with user-facing error. DB state verified after each move. Blocker validation confirmed. | Epic 5: QA & Testing | QA | 5 | P1 | Sprint 3 | FE-03, BE-03 | Not Started
QA-06 | E2E test — Gantt chart | Playwright script: Create project with milestone → Set RAID risk → Verify Gantt renders bar, milestone diamond, and RAID flag. Set date to past milestone → Verify diamond pulses. | All three Gantt signals render correctly in Playwright. RAID flag appears at correct date position. Overdue milestone diamond pulse verified. Tooltip content verified. | Epic 5: QA & Testing | QA | 5 | P1 | Sprint 4 | FE-04, BE-10 | Not Started
QA-07 | Security penetration test | Attempt: (1) Access budget data as Member. (2) Access another user's project. (3) Manually override RAG without Admin role. (4) Modify or delete audit log entry. (5) Bypass Kanban blocker validation via direct API call. | All five attack vectors rejected. System returns appropriate error codes. No data leakage in error messages. All attempts logged to audit trail. | Epic 5: QA & Testing | QA/SEC | 5 | P0 | Sprint 4 | SEC-01–06 | Not Started
QA-08 | Performance testing | Load test portfolio dashboard with 500 active projects. Load test RAG recalculation under concurrent task updates. Load test Gantt endpoint with 100 projects and dependencies. | Portfolio dashboard < 2s P95 at 500 projects. RAG recalculation < 500ms. Gantt endpoint < 3s at 100 projects. No memory leaks over 1-hour sustained load. | Epic 5: QA & Testing | QA/DEVOPS | 5 | P1 | Sprint 4 | BE-09, BE-10 | Not Started | NFR targets from §2.2.1 of spec.
QA-09 | UAT — Project Managers | PMs use real projects in Staging: create a project, track tasks on Kanban, log RAID items, view Gantt, approve a gate review, export a report. | Head of Operations signs off on UAT script completion. All critical user journeys completed without workarounds. Bug severity P0/P1 count: zero. | Epic 5: QA & Testing | QA/PM | 3 | P0 | Sprint 4 | FE-01–15, BE-01–16 | Not Started | Sign-off required before OPS-02 (production migration) is scheduled.
OPS-01 | Feature flag setup | Wrap entire PPM module in ENABLE_PPM feature flag using LaunchDarkly or equivalent. Module must be completely invisible when flag is false. | PPM module invisible (no routes, no API endpoints, no DB queries) when flag disabled. Tested in staging with flag both on and off. Flag can be toggled per environment. | Epic 6: Deployment | DEVOPS | 2 | P0 | Sprint 1 |  | Not Started
OPS-02 | Production migration + rollback plan | Run Prisma migrations on production DB. Zero-downtime migration using expand-contract pattern. Rollback script tested in staging before production run. | Migrations run with zero downtime or in documented maintenance window. Rollback script tested in staging and documented. Post-migration smoke test passes. Monitoring confirms no performance degradation. | Epic 6: Deployment | DEVOPS | 5 | P0 | Sprint 5 | QA-09 | Not Started | Rollback plan was absent in v1 spec. Must be authored and tested in staging before production deployment.
OPS-03 | Performance monitoring setup | Configure monitoring alerts: RAG calculation query >500ms, portfolio dashboard >2s, Gantt endpoint >3s. Dashboard in monitoring tool showing key query performance. | All three alert thresholds configured. Monitoring dashboard live. Alert notification routes configured. Baseline metrics captured from staging load test. | Epic 6: Deployment | DEVOPS | 3 | P1 | Sprint 4 | QA-08 | Not Started
OPS-04 | User training programme | Conduct workshop with Project Managers covering: Kanban workflow, RAID logging, Gantt reading, gate review process. Produce training materials and video walkthroughs. | Workshop completed. Training materials published to internal wiki. PM team confirms understanding of all four workflows. At least 80% of PMs complete self-assessment quiz. | Epic 6: Deployment | PM | 3 | P1 | Sprint 5 | QA-09 | Not Started
OPS-05 | Phase 1 rollout — Engineering pilot | Enable PPM for Engineering team only via feature flag. Migrate active Engineering projects from CSV. Collect velocity data for Monte Carlo baseline. | Engineering projects migrated. Feature flag enabled for Engineering role. Velocity data collection running. 3-sprint data baseline target set for Phase 2. | Epic 6: Deployment | DEVOPS/PM | 3 | P0 | Sprint 5 | OPS-02, OPS-04 | Not Started

## Sprint Plan
VF-OPS-001 — Sprint Plan
Sprint | Focus | Task ID | Title | Role | SP
Sprint 0 | Pre-sprint · Dependency contracts, shared model agreement, schema authoring | INF-03 | Shared User Model contract | BE | 2
|  |  | Sprint total |  | 2
Sprint 1 | Epic 1 + Epic 2 (BE-01/03) + Epic 4 (SEC-01/03/04/05) + OPS-01 | DB-01 | Prisma schema — base PPM models | DB | 5
|  | DB-02 | Prisma schema — premium models | DB | 8
|  | DB-03 | Seed script — initial data | DB | 2
|  | INF-01 | S3 configuration for project files | DEVOPS | 2
|  | INF-02 | Notification service integration | BE | 3
|  | BE-01 | Project CRUD endpoints | BE | 5
|  | BE-03 | Kanban state machine | BE | 5
|  | SEC-01 | API role guards | BE | 5
|  | SEC-03 | Audit log integrity enforcement | BE | 2
|  | SEC-04 | Data isolation — project visibility | BE | 5
|  | SEC-05 | OpenAPI spec generation | BE | 5
|  | OPS-01 | Feature flag setup | DEVOPS | 2
|  |  | Sprint total |  | 49
Sprint 2 | Epic 2 (BE-02/04/05/06/08/09) + Epic 3 (FE-01/02/03/10) + SEC-02/06 + QA-01/02 | BE-02 | RAG calculation engine | BE | 8
|  | BE-04 | RAID log management | BE | 5
|  | BE-05 | Budget tracking service | BE | 5
|  | BE-06 | Resource assignment service | BE | 3
|  | BE-07 | File attachment service | BE | 5
|  | BE-08 | Audit logging interceptor | BE | 5
|  | BE-09 | Portfolio aggregation API | BE | 5
|  | FE-01 | Portfolio dashboard page | FE | 8
|  | FE-02 | Project workspace layout | FE | 5
|  | FE-03 | Kanban board component | FE | 13
|  | FE-10 | RBAC frontend guards | FE | 5
|  | SEC-02 | Budget data access control | BE | 3
|  | SEC-06 | Manual RAG override controls | BE+FE | 3
|  | QA-01 | Unit tests — RAG logic | QA/BE | 5
|  | QA-02 | Unit tests — Kanban state machine | QA/BE | 3
|  |  | Sprint total |  | 81
Sprint 3 | Epic 2 (BE-10/16) + Epic 3 (FE-04/06/07/08/09/11) + QA-03/04/05 | BE-10 | Gantt data API | BE | 8
|  | BE-11 | Cross-project dependency engine | BE | 8
|  | BE-16 | Export service — PDF and CSV | BE | 5
|  | FE-04 | Gantt chart — static rendering | FE | 21
|  | FE-06 | RAID log data grid | FE | 8
|  | FE-07 | Budget chart component | FE | 5
|  | FE-08 | Project creation wizard | FE | 8
|  | FE-09 | Task detail modal | FE | 5
|  | FE-11 | File upload component | FE | 3
|  | QA-03 | Integration tests — core flows | QA/BE | 8
|  | QA-04 | Integration tests — RBAC flows | QA/BE | 5
|  | QA-05 | E2E test — Kanban workflow | QA | 5
|  |  | Sprint total |  | 89
Sprint 4 | Epic 2 (BE-11/12/13/14/15/17) + Epic 3 (FE-05/12/13/15) + QA-06/07/08/09 + OPS-03 | BE-12 | Monte Carlo forecast service | BE | 13
|  | BE-13 | Gate review workflow | BE | 8
|  | BE-14 | Capacity planning service | BE | 5
|  | BE-15 | OKR alignment service | BE | 5
|  | BE-17 | Notification preferences service | BE | 3
|  | FE-05 | Gantt chart — drag-to-reschedule | FE | 13
|  | FE-12 | Capacity planning grid | FE | 8
|  | FE-13 | Dependency graph view | FE | 13
|  | FE-15 | Gate review panel | FE | 5
|  | QA-06 | E2E test — Gantt chart | QA | 5
|  | QA-07 | Security penetration test | QA/SEC | 5
|  | QA-08 | Performance testing | QA/DEVOPS | 5
|  | QA-09 | UAT — Project Managers | QA/PM | 3
|  | OPS-03 | Performance monitoring setup | DEVOPS | 3
|  |  | Sprint total |  | 94
Sprint 5 | Epic 3 (FE-14/16/17) + Epic 6 (OPS-02/04/05) — Phase 1 rollout | FE-14 | Public status page builder | FE | 8
|  | FE-16 | Velocity analytics dashboard | FE | 8
|  | FE-17 | Prioritisation scoring matrix | FE | 8
|  | OPS-02 | Production migration + rollback plan | DEVOPS | 5
|  | OPS-04 | User training programme | PM | 3
|  | OPS-05 | Phase 1 rollout — Engineering pilot | DEVOPS/PM | 3
|  |  | Sprint total |  | 35

## Epic Summary
VF-OPS-001 — Epic Summary
Epic | Total Tasks | P0 Tasks | P1 Tasks | P2 Tasks | Total SP | Avg SP
Epic 1: Foundation | 6 | 3 | 3 | 0 | 22 | 3.7
Epic 2: Backend | 17 | 5 | 9 | 3 | 101 | 5.9
Epic 3: Frontend | 17 | 6 | 7 | 4 | 144 | 8.5
Epic 4: Security | 6 | 4 | 2 | 0 | 23 | 3.8
Epic 5: QA & Testing | 9 | 2 | 7 | 0 | 44 | 4.9
Epic 6: Deployment | 5 | 3 | 2 | 0 | 16 | 3.2
TOTAL | 60 | 23 | 30 | 7 | 350 | 5.8

## Dependency Map
VF-OPS-001 — Dependency Map
Task ID | Task Title | Depends On | Blocked By | Sprint
DB-02 | Prisma schema — premium models | DB-01 | Blocked | Sprint 1
DB-03 | Seed script — initial data | DB-01 | Blocked | Sprint 1
BE-01 | Project CRUD endpoints | DB-01 | Blocked | Sprint 1
BE-02 | RAG calculation engine | BE-01, DB-01 | Blocked | Sprint 2
BE-03 | Kanban state machine | DB-01 | Blocked | Sprint 1
BE-04 | RAID log management | BE-01 | Blocked | Sprint 2
BE-05 | Budget tracking service | BE-01, BE-02 | Blocked | Sprint 2
BE-06 | Resource assignment service | DB-01 | Blocked | Sprint 2
BE-07 | File attachment service | INF-01 | Blocked | Sprint 2
BE-08 | Audit logging interceptor | DB-01 | Blocked | Sprint 2
BE-09 | Portfolio aggregation API | BE-01, BE-02 | Blocked | Sprint 2
BE-10 | Gantt data API | BE-01, BE-11, BE-12 | Blocked | Sprint 3
BE-11 | Cross-project dependency engine | DB-02 | Blocked | Sprint 3
BE-12 | Monte Carlo forecast service | DB-02, BE-10 | Blocked | Sprint 4
BE-13 | Gate review workflow | DB-02, BE-08 | Blocked | Sprint 4
BE-14 | Capacity planning service | BE-06, DB-02 | Blocked | Sprint 4
BE-15 | OKR alignment service | DB-02 | Blocked | Sprint 4
BE-16 | Export service — PDF and CSV | BE-01, BE-04, BE-05 | Blocked | Sprint 3
BE-17 | Notification preferences service | INF-02 | Blocked | Sprint 4
FE-01 | Portfolio dashboard page | BE-09 | Blocked | Sprint 2
FE-02 | Project workspace layout | BE-01 | Blocked | Sprint 2
FE-03 | Kanban board component | BE-03, FE-02 | Blocked | Sprint 2
FE-04 | Gantt chart — static rendering | BE-10 | Blocked | Sprint 3
FE-05 | Gantt chart — drag-to-reschedule | FE-04, BE-11 | Blocked | Sprint 4
FE-06 | RAID log data grid | BE-04, FE-02 | Blocked | Sprint 3
FE-07 | Budget chart component | BE-05, FE-02 | Blocked | Sprint 3
FE-08 | Project creation wizard | BE-01, BE-15 | Blocked | Sprint 3
FE-09 | Task detail modal | BE-03, BE-07, FE-03 | Blocked | Sprint 3
FE-10 | RBAC frontend guards | INF-03 | Blocked | Sprint 2
FE-11 | File upload component | BE-07 | Blocked | Sprint 3
FE-12 | Capacity planning grid | BE-14, FE-01 | Blocked | Sprint 4
FE-13 | Dependency graph view | BE-11, FE-04 | Blocked | Sprint 4
FE-14 | Public status page builder | BE-01, FE-02 | Blocked | Sprint 5
FE-15 | Gate review panel | BE-13, FE-02 | Blocked | Sprint 4
FE-16 | Velocity analytics dashboard | BE-12 | Blocked | Sprint 5
FE-17 | Prioritisation scoring matrix | BE-15 | Blocked | Sprint 5
SEC-01 | API role guards | INF-03 | Blocked | Sprint 1
SEC-02 | Budget data access control | SEC-01 | Blocked | Sprint 2
SEC-03 | Audit log integrity enforcement | BE-08 | Blocked | Sprint 1
SEC-04 | Data isolation — project visibility | DB-01 | Blocked | Sprint 1
SEC-05 | OpenAPI spec generation | BE-01 | Blocked | Sprint 1
SEC-06 | Manual RAG override controls | BE-02, SEC-01 | Blocked | Sprint 2
QA-01 | Unit tests — RAG logic | BE-02 | Blocked | Sprint 2
QA-02 | Unit tests — Kanban state machine | BE-03 | Blocked | Sprint 2
QA-03 | Integration tests — core flows | BE-01, BE-02, BE-05 | Blocked | Sprint 3
QA-04 | Integration tests — RBAC flows | SEC-01, SEC-04 | Blocked | Sprint 3
QA-05 | E2E test — Kanban workflow | FE-03, BE-03 | Blocked | Sprint 3
QA-06 | E2E test — Gantt chart | FE-04, BE-10 | Blocked | Sprint 4
QA-07 | Security penetration test | SEC-01–06 | Blocked | Sprint 4
QA-08 | Performance testing | BE-09, BE-10 | Blocked | Sprint 4
QA-09 | UAT — Project Managers | FE-01–15, BE-01–16 | Blocked | Sprint 4
OPS-02 | Production migration + rollback plan | QA-09 | Blocked | Sprint 5
OPS-03 | Performance monitoring setup | QA-08 | Blocked | Sprint 4
OPS-04 | User training programme | QA-09 | Blocked | Sprint 5
OPS-05 | Phase 1 rollout — Engineering pilot | OPS-02, OPS-04 | Blocked | Sprint 5
DB-01 | Prisma schema — base PPM models |  |  | Sprint 1
INF-01 | S3 configuration for project files |  |  | Sprint 1
INF-02 | Notification service integration |  |  | Sprint 1
INF-03 | Shared User Model contract |  |  | Sprint 0
OPS-01 | Feature flag setup |  |  | Sprint 1

## Dashboard
VF-OPS-001 — Task Metrics Dashboard
Total Tasks |  | Total Story Points |  | P0 Release Blockers |  | Sprints Planned
60 |  | 350 |  | 23 |  | 6
across all epics |  | estimated effort |  | must ship in v1 |  | Sprint 0 to Sprint 5
Backend Tasks |  | Frontend Tasks |  | QA Tasks |  | Avg SP per Task
29 |  | 18 |  | 9 |  | 5.8
BE / DB / DEVOPS |  | FE role |  | testing & security |  | story point density
Story Points by Epic |  |  | Story Points by Sprint |  | Tasks by Priority
Foundation | 22 |  | Sprint 0 | 2 | P0 — Release Blocker |  | 23
Backend | 101 |  | Sprint 1 | 49 | P1 — High |  | 30
Frontend | 144 |  | Sprint 2 | 81 | P2 — Nice to Have |  | 7
Security | 23 |  | Sprint 3 | 89
QA & Testing | 44 |  | Sprint 4 | 94
Deployment | 16 |  | Sprint 5 | 35